## GMS
SR.NO | Issue | System | Resolution | Considered In Code | Update in Operational Guide
1) | Gateway name mismatch at Jenkins Global variable (DIDGateway) | GMS | Modified | Y
2) | Modified SQL for Index creation in NRMA_GMS_CREATE_PRUNE_INDEX file | GMS | Modified in File | Y
3) | Performance issue in PRUNE_DOC_AGREE_JOB | GMS | Recent Index is got created S_AGREE_BNFT_F8_X Dropped it.
4) | In SR_VALDN Job Input DID_GMS_REMOTE_HOST was missed | GMS | Added | Y
5) | System DB_STATS are not disabled | GMS/GFS/OCH | Disable by Nitin |  | Y
6) | EVT ACT Drop Index Failed dute to typo | GMS | Modified | Y
7) | DROP Index File Modified For Activity | GMS | Modified | Y
8) | Table_Name in FK asset prcd | GMS | Modifed to new table name | Y
9) | INDEX DROPPED ON Asset_XA | GMS | Removed from file also | Y
10) | Indexes On Activity got dropped which were needed | GMS | Added and removed from SQL File | Y
11) | Account Indexes didnt got dropped | GMS | Modified SQL File names | Y
12) | In Indexs Shell file format issue | GMS | Converted DOS to UNIX |  | Y
13) | In SRC Masking Master count job Date missed | GMS | Added | Y
14) | 83 DUP_RECORD_EXISTS on org_ext validation | GMS | master count sh modified to add not in EIM (Duplicate userkeys exists) | Y
15) | DID_GMS_41_B_ORG_EXT_UK_STAGING_INSERT in this job one extra input passed | GMS | Removed | Y
16) | Need to create Index On ACCNT_UK temp table as performance issue | GMS | Created | Y
17) | GMS MASK Contact job Enterprise name came two times | GMS | Removed one | Y

## OCH
SR.NO | Issue | Resolution | Considered In Code | Update in Operational Guide
1) | Table creation Script For Temp Table, Column misplaced | Modified | Y
2) | Two times index creation came in Jen Job and Procd | Removed Index Craetion From Proc | Y
3) | SIF Import not done in OCH | Done |  | Y
4) | System DB_STATS are not disabled | Disable by Nitin |  | Y
5) | NRMA_ENV_BATCH_EXPORT_SH | Name mismatch in initial two jobs modified those | Y
6) | For Pruning ADDR_PER validation reduced % to 95 as some record failing with dup_record_exists | Reduced % to 95 (Duplicate userkeys exists) | Y
7) | EIM_ASSET_X Master count check Table mismatch | Modified | Y
8) | DID_OCH_17_A_S_DQ_ORAG_KEY_DB_STATS in this job remote_host global var missed | Added | Y
9) | Org_Ext Pruning taking time | Added Indexes on PR_BL_OU_ID,PR_SHIP_OU_ID, PR_COMPETITOR_ID(Updated SQL File also) | Y
10) | Need to create Index On ACCNT_UK temp table as performance issue | Created | Y
11) | org_ext uk insert failed | New table name in procd missed , added | Y

## GFS
SR.NO | Issue |  | Resolution | Update in Operational Guide
1) | REMOTE HOST KEY IS NOT UPDATED WITH THE RIGHT VALUE |  | FIXED BY PROVIDING THE RIGHT VALUE
2) | REMOTE HOST IS NOT UPDATED WITH THE RIGHT VALUE |  | FIXED BY PROVIDING THE RIGHT VALUE
3) | SELECT QUERY RESULTED 0 RECORDS IN CREATE_XX_CUST_ACCOUNT_ID | BECAUSE OF NULL VALUES IN THE FILE SHARED BY GMS | FIXED BY ADDING NOT NULL CLAUSE TO THE QUERY
4) | .sh file is not recognising the profile file |  | Fixed by copying the same from the other succesful file | Y
5) | Permission denied for expdp/impdp | insufficient privileges | fixed by granting execute privileges for oracle user for expdp/imdp
6) | The export process is very slow | Due to less amount of memory which is 8 GB | fixed by increasing it to 40 GB
7) | The application has to be brought down before invoking the DID jobs |  |  | Y
8) | The performane of Import of XLA_DISTRIBUTION_LINKS is very low

## Ponits_To_Consider
1. DUP_RECORD_EXISTS Error: In Masking the tables S_ADDR_PER,S_ORG_EXT,S_SRV_REQ_X are being effected with DUP_RECORD_EXISTS error. The reason is, Data exists with duplicate userkeys.
2. AMBIGUOUS Error: In Masking of S_ADDR_PER records failing with AMBIGUOUS status. As analyzed found that data having same userkeys but differrnt conflit Id's are failing with this stats.
Note: The records effected are very less with above status. Hence, ignorable.
3. In GMS Masking 2 tables were skipped S_AGREE_BNFT and S_ORDER_X, Found that no sensitive or PII data exists. S_AGREE_BNFT table contains NAME attribute which has repeated data and considered as not PII/Sensitive data. In S_ORDER_X table ATTRIB_39 attribute contains Id's, So not considered for Masking.